## 📅 Daily View
📅 Daily View ¦ Start: 06 Jan 2025 ¦ 6.0h/day ¦ Total: 410h
Summary | Assignee | Priority | Original Estimate (hrs) | Day1 6 Jan | Day2 7 Jan | Day3 8 Jan | Day4 9 Jan | Day5 10 Jan | Day6 13 Jan | Day7 14 Jan | Day8 15 Jan | Day9 16 Jan | Day10 17 Jan | Day11 20 Jan | Day12 21 Jan | Day13 22 Jan | Day14 23 Jan | Day15 24 Jan | Day16 27 Jan | Day17 28 Jan | Day18 29 Jan | Day19 30 Jan | Day20 31 Jan | Day21 3 Feb | Day22 4 Feb | Day23 5 Feb | Day24 6 Feb | Day25 7 Feb | Day26 10 Feb | Day27 11 Feb | Day28 12 Feb | Day29 13 Feb | Day30 14 Feb | Day31 17 Feb | Day32 18 Feb | Day33 19 Feb | Day34 20 Feb | Day35 21 Feb | Day36 24 Feb | Day37 25 Feb | Day38 26 Feb | Day39 27 Feb | Day40 28 Feb | Day41 3 Mar | Day42 4 Mar | Day43 5 Mar | Day44 6 Mar | Day45 7 Mar | Day46 10 Mar | Day47 11 Mar | Day48 12 Mar | Day49 13 Mar | Day50 14 Mar | Day51 17 Mar | Day52 18 Mar | Day53 19 Mar | Day54 20 Mar | Day55 21 Mar | Day56 24 Mar | Day57 25 Mar | Day58 26 Mar | Day59 27 Mar | Day60 28 Mar | Day61 31 Mar | Day62 1 Apr | Day63 2 Apr | Day64 3 Apr | Day65 4 Apr | Day66 7 Apr | Day67 8 Apr | Day68 9 Apr | Day69 10 Apr
Design And requirement Analysis | Arka/Tamal | 1 | 20 | 6 | 6 | 6 | 2
Skeleton Setup | Arka/Tamal | 1 | 10 |  |  |  | 4 | 6
Define overall system architecture | Arka/Tamal | 2 | 2 | [5 empty] | 2
Define agent responsibilities | Arka/Tamal | 2 | 1 | [5 empty] | 1
Define chain responsibilities | Arka/Tamal | 2 | 1 | [5 empty] | 1
Define tool interfaces | Arka/Tamal | 2 | 1 | [5 empty] | 1
Define state model | Arka/Tamal | 2 | 2 | [5 empty] | 1 | 1
Setup graph project structure | Arka/Tamal | 2 | 2 | [6 empty] | 2
Implement graph node abstraction | Arka/Tamal | 2 | 2 | [6 empty] | 2
Implement routing layer | Arka/Tamal | 2 | 2 | [6 empty] | 1 | 1
Implement node transitions | Arka/Tamal | 2 | 2 | [7 empty] | 2
Implement session lifecycle | Arka/Tamal | 2 | 2 | [7 empty] | 2
Integrate graph state store | Arka/Tamal | 2 | 1 | [7 empty] | 1
Validate graph execution flow | Arka/Tamal | 2 | 1 | [8 empty] | 1
Design session schema | Arka/Tamal | 3 | 4 | [8 empty] | 4
Design state variable schema | Arka/Tamal | 3 | 2 | [8 empty] | 1 | 1
Implement DB connection layer | Arka/Tamal | 3 | 2 | [9 empty] | 2
Implement session storage | Arka/Tamal | 3 | 3 | [9 empty] | 3
Implement conversation history storage | Arka/Tamal | 3 | 3 | [10 empty] | 3
Implement state serialization | Arka/Tamal | 3 | 3 | [10 empty] | 3
Implement state retrieval | Arka/Tamal | 3 | 3 | [11 empty] | 3
Implement state update logic | Arka/Tamal | 3 | 3 | [11 empty] | 3
Implement session recovery | Arka/Tamal | 3 | 3 | [12 empty] | 3
Implement state expiration | Arka/Tamal | 3 | 2 | [12 empty] | 2
DB error handling | Arka/Tamal | 3 | 2 | [12 empty] | 1 | 1
Implement age verification flow | Arka/Tamal | 4 | 2 | [13 empty] | 2
Implement intent classification | Arka/Tamal | 4 | 2 | [13 empty] | 2
Implement ambiguity detection | Arka/Tamal | 4 | 2 | [13 empty] | 1 | 1
Implement routing logic | Arka/Tamal | 4 | 2 | [14 empty] | 2
Implement fallback routing | Arka/Tamal | 4 | 2 | [14 empty] | 2
Event parameter extraction | Arka/Tamal | 5 | 2 | [14 empty] | 1 | 1
Budget validation logic | Arka/Tamal | 5 | 2 | [15 empty] | 2
Cocktail mode handling | Arka/Tamal | 5 | 2 | [15 empty] | 2
Drink calculation logic | Arka/Tamal | 5 | 2 | [15 empty] | 1 | 1
Category budget allocation | Arka/Tamal | 5 | 2 | [16 empty] | 2
Inventory search orchestration | Arka/Tamal | 5 | 2 | [16 empty] | 2
Package builder | Arka/Tamal | 5 | 2 | [16 empty] | 1 | 1
Modification handling | Arka/Tamal | 5 | 1 | [17 empty] | 1
Delivery detail collection | Arka/Tamal | 5 | 1 | [17 empty] | 1
Product query parsing | Arka/Tamal | 6 | 2 | [17 empty] | 2
Inventory lookup | Arka/Tamal | 6 | 2 | [17 empty] | 1 | 1
Recommendation logic | Arka/Tamal | 6 | 2 | [18 empty] | 2
Similar product suggestion | Arka/Tamal | 6 | 2 | [18 empty] | 2
Supplies recommendation | Arka/Tamal | 7 | 2 | [18 empty] | 1 | 1
OOS handling | Arka/Tamal | 7 | 2 | [19 empty] | 2
Budget recalculation | Arka/Tamal | 7 | 2 | [19 empty] | 2
Staffing offer | Arka/Tamal | 7 | 1 | [19 empty] | 1
Menu email option | Arka/Tamal | 7 | 1 | [20 empty] | 1
Info extraction chain | Arka/Tamal | 8 | 3 | [20 empty] | 3
Budget viability chain | Arka/Tamal | 8 | 3 | [20 empty] | 2 | 1
Cocktail adjustment chain | Arka/Tamal | 8 | 3 | [21 empty] | 3
Drink calculation chain | Arka/Tamal | 8 | 3 | [21 empty] | 2 | 1
Category budget chain | Arka/Tamal | 8 | 3 | [22 empty] | 3
Inventory search chain | Arka/Tamal | 8 | 4 | [22 empty] | 2 | 2
Package assembly chain | Arka/Tamal | 8 | 4 | [23 empty] | 4
Budget compliance chain | Arka/Tamal | 8 | 3 | [24 empty] | 3
Delivery chain | Arka/Tamal | 8 | 2 | [24 empty] | 2
Query parsing chain | Arka/Tamal | 9 | 3 | [24 empty] | 1 | 2
Inventory search chain | Arka/Tamal | 9 | 3 | [25 empty] | 3
Recommendation chain | Arka/Tamal | 9 | 4 | [25 empty] | 1 | 3
Similarity chain | Arka/Tamal | 9 | 3 | [26 empty] | 3
Product request chain | Arka/Tamal | 9 | 2 | [27 empty] | 2
Supplies search chain | Arka/Tamal | 10 | 3 | [27 empty] | 3
OOS handling chain | Arka/Tamal | 10 | 3 | [27 empty] | 1 | 2
Budget adjustment chain | Arka/Tamal | 10 | 3 | [28 empty] | 3
Staffing chain | Arka/Tamal | 10 | 3 | [28 empty] | 1 | 2
Menu email chain | Arka/Tamal | 10 | 2 | [29 empty] | 2
Chain orchestration wiring | Arka/Tamal | 11 | 3 | [29 empty] | 2 | 1
Inventory API wrapper | Arka/Tamal | 12 | 4 | [30 empty] | 4
Product classification | Arka/Tamal | 12 | 3 | [30 empty] | 1 | 2
Sorting algorithm | Arka/Tamal | 12 | 2 | [31 empty] | 2
Deduplication logic | Arka/Tamal | 12 | 3 | [31 empty] | 2 | 1
Stock verification | Arka/Tamal | 12 | 2 | [32 empty] | 2
History API wrapper | Arka/Tamal | 13 | 3 | [32 empty] | 3
Preference parsing | Arka/Tamal | 13 | 3 | [33 empty] | 3
Fallback logic | Arka/Tamal | 13 | 2 | [33 empty] | 2
Email builder | Arka/Tamal | 14 | 2 | [33 empty] | 1 | 1
Multi-recipient logic | Arka/Tamal | 14 | 2 | [34 empty] | 2
Failure handling | Arka/Tamal | 14 | 2 | [34 empty] | 2
Base behavior prompt | Arka/Tamal | 15 | 6 | [34 empty] | 1 | 5
Safety rules prompt | Arka/Tamal | 15 | 6 | [35 empty] | 1 | 5
Tool usage prompt | Arka/Tamal | 15 | 6 | [36 empty] | 1 | 5
Conversation style prompt | Arka/Tamal | 15 | 4 | [37 empty] | 1 | 3
Domain prompt | Arka/Tamal | 15 | 3 | [38 empty] | 3
Orchestrator role prompt | Arka/Tamal | 15 | 3 | [39 empty] | 3
Event planner prompt | Arka/Tamal | 15 | 5 | [39 empty] | 3 | 2
Product search prompt | Arka/Tamal | 15 | 3 | [40 empty] | 3
Supplies prompt | Arka/Tamal | 15 | 3 | [40 empty] | 1 | 2
Edge case tuning | Arka/Tamal | 15 | 3 | [41 empty] | 3
Routing tuning | Arka/Tamal | 15 | 2 | [41 empty] | 1 | 1
Regression tuning | Arka/Tamal | 15 | 1 | [42 empty] | 1
Agent unit tests | Arka/Tamal | 16 | 18 | [42 empty] | 4 | 6 | 6 | 2
Chain unit tests | Arka/Tamal | 16 | 20 | [45 empty] | 4 | 6 | 6 | 4
Tool unit tests | Arka/Tamal | 16 | 12 | [48 empty] | 2 | 6 | 4
Graph tests | Arka/Tamal | 16 | 8 | [50 empty] | 2 | 6
State tests | Arka/Tamal | 16 | 6 | [52 empty] | 6
Fixtures | Arka/Tamal | 16 | 8 | [53 empty] | 6 | 2
Conversation fixtures | Arka/Tamal | 17 | 8 | [54 empty] | 4 | 4
Mock responses | Arka/Tamal | 17 | 6 | [55 empty] | 2 | 4
Scenario tests | Arka/Tamal | 17 | 10 | [56 empty] | 2 | 6 | 2
Test harness | Arka/Tamal | 17 | 6 | [58 empty] | 4 | 2
Inventory mock | Arka/Tamal | 18 | 4 | [59 empty] | 4
History mock | Arka/Tamal | 18 | 3 | [60 empty] | 3
Email mock | Arka/Tamal | 18 | 3 | [60 empty] | 3
Test data generator | Arka/Tamal | 18 | 2 | [61 empty] | 2
Retry logic | Arka/Tamal | 19 | 4 | [61 empty] | 4
Rate limit handling | Arka/Tamal | 19 | 4 | [62 empty] | 4
Fallback logic | Arka/Tamal | 19 | 4 | [62 empty] | 2 | 2
Tracing integration | Arka/Tamal | 20 | 3 | [63 empty] | 3
Evaluation metrics | Arka/Tamal | 20 | 3 | [63 empty] | 1 | 2
Architecture documentation | Arka/Tamal | 21 | 8 | [64 empty] | 4 | 4
Developer setup guide | Arka/Tamal | 21 | 6 | [65 empty] | 2 | 4
Testing documentation | Arka/Tamal | 21 | 4 | [66 empty] | 2 | 2
API documentation | Arka/Tamal | 21 | 4 | [67 empty] | 4
Operational notes | Arka/Tamal | 21 | 2 | [68 empty] | 2
TOTAL HOURS |  |  | 410
Cell value = hours worked in that period ¦ Color = priority level

## 📆 Weekly View
📆 Weekly View ¦ Start: 06 Jan 2025 ¦ 6.0h/day ¦ Total: 410h
Summary | Assignee | Priority | Original Estimate (hrs) | Wk1 6 Jan | Wk2 13 Jan | Wk3 20 Jan | Wk4 27 Jan | Wk5 3 Feb | Wk6 10 Feb | Wk7 17 Feb | Wk8 24 Feb | Wk9 3 Mar | Wk10 10 Mar | Wk11 17 Mar | Wk12 24 Mar | Wk13 31 Mar | Wk14 7 Apr | Wk15 14 Apr
Design And requirement Analysis | Arka/Tamal | 1 | 20 | 20
Skeleton Setup | Arka/Tamal | 1 | 10 | 10
Define overall system architecture | Arka/Tamal | 2 | 2 |  | 2
Define agent responsibilities | Arka/Tamal | 2 | 1 |  | 1
Define chain responsibilities | Arka/Tamal | 2 | 1 |  | 1
Define tool interfaces | Arka/Tamal | 2 | 1 |  | 1
Define state model | Arka/Tamal | 2 | 2 |  | 2
Setup graph project structure | Arka/Tamal | 2 | 2 |  | 2
Implement graph node abstraction | Arka/Tamal | 2 | 2 |  | 2
Implement routing layer | Arka/Tamal | 2 | 2 |  | 2
Implement node transitions | Arka/Tamal | 2 | 2 |  | 2
Implement session lifecycle | Arka/Tamal | 2 | 2 |  | 2
Integrate graph state store | Arka/Tamal | 2 | 1 |  | 1
Validate graph execution flow | Arka/Tamal | 2 | 1 |  | 1
Design session schema | Arka/Tamal | 3 | 4 |  | 4
Design state variable schema | Arka/Tamal | 3 | 2 |  | 2
Implement DB connection layer | Arka/Tamal | 3 | 2 |  | 2
Implement session storage | Arka/Tamal | 3 | 3 |  | 3
Implement conversation history storage | Arka/Tamal | 3 | 3 |  |  | 3
Implement state serialization | Arka/Tamal | 3 | 3 |  |  | 3
Implement state retrieval | Arka/Tamal | 3 | 3 |  |  | 3
Implement state update logic | Arka/Tamal | 3 | 3 |  |  | 3
Implement session recovery | Arka/Tamal | 3 | 3 |  |  | 3
Implement state expiration | Arka/Tamal | 3 | 2 |  |  | 2
DB error handling | Arka/Tamal | 3 | 2 |  |  | 2
Implement age verification flow | Arka/Tamal | 4 | 2 |  |  | 2
Implement intent classification | Arka/Tamal | 4 | 2 |  |  | 2
Implement ambiguity detection | Arka/Tamal | 4 | 2 |  |  | 2
Implement routing logic | Arka/Tamal | 4 | 2 |  |  | 2
Implement fallback routing | Arka/Tamal | 4 | 2 |  |  | 2
Event parameter extraction | Arka/Tamal | 5 | 2 |  |  | 1 | 1
Budget validation logic | Arka/Tamal | 5 | 2 |  |  |  | 2
Cocktail mode handling | Arka/Tamal | 5 | 2 |  |  |  | 2
Drink calculation logic | Arka/Tamal | 5 | 2 |  |  |  | 2
Category budget allocation | Arka/Tamal | 5 | 2 |  |  |  | 2
Inventory search orchestration | Arka/Tamal | 5 | 2 |  |  |  | 2
Package builder | Arka/Tamal | 5 | 2 |  |  |  | 2
Modification handling | Arka/Tamal | 5 | 1 |  |  |  | 1
Delivery detail collection | Arka/Tamal | 5 | 1 |  |  |  | 1
Product query parsing | Arka/Tamal | 6 | 2 |  |  |  | 2
Inventory lookup | Arka/Tamal | 6 | 2 |  |  |  | 2
Recommendation logic | Arka/Tamal | 6 | 2 |  |  |  | 2
Similar product suggestion | Arka/Tamal | 6 | 2 |  |  |  | 2
Supplies recommendation | Arka/Tamal | 7 | 2 |  |  |  | 2
OOS handling | Arka/Tamal | 7 | 2 |  |  |  | 2
Budget recalculation | Arka/Tamal | 7 | 2 |  |  |  | 2
Staffing offer | Arka/Tamal | 7 | 1 |  |  |  | 1
Menu email option | Arka/Tamal | 7 | 1 |  |  |  |  | 1
Info extraction chain | Arka/Tamal | 8 | 3 |  |  |  |  | 3
Budget viability chain | Arka/Tamal | 8 | 3 |  |  |  |  | 3
Cocktail adjustment chain | Arka/Tamal | 8 | 3 |  |  |  |  | 3
Drink calculation chain | Arka/Tamal | 8 | 3 |  |  |  |  | 3
Category budget chain | Arka/Tamal | 8 | 3 |  |  |  |  | 3
Inventory search chain | Arka/Tamal | 8 | 4 |  |  |  |  | 4
Package assembly chain | Arka/Tamal | 8 | 4 |  |  |  |  | 4
Budget compliance chain | Arka/Tamal | 8 | 3 |  |  |  |  | 3
Delivery chain | Arka/Tamal | 8 | 2 |  |  |  |  | 2
Query parsing chain | Arka/Tamal | 9 | 3 |  |  |  |  | 1 | 2
Inventory search chain | Arka/Tamal | 9 | 3 | [5 empty] | 3
Recommendation chain | Arka/Tamal | 9 | 4 | [5 empty] | 4
Similarity chain | Arka/Tamal | 9 | 3 | [5 empty] | 3
Product request chain | Arka/Tamal | 9 | 2 | [5 empty] | 2
Supplies search chain | Arka/Tamal | 10 | 3 | [5 empty] | 3
OOS handling chain | Arka/Tamal | 10 | 3 | [5 empty] | 3
Budget adjustment chain | Arka/Tamal | 10 | 3 | [5 empty] | 3
Staffing chain | Arka/Tamal | 10 | 3 | [5 empty] | 3
Menu email chain | Arka/Tamal | 10 | 2 | [5 empty] | 2
Chain orchestration wiring | Arka/Tamal | 11 | 3 | [5 empty] | 2 | 1
Inventory API wrapper | Arka/Tamal | 12 | 4 | [6 empty] | 4
Product classification | Arka/Tamal | 12 | 3 | [6 empty] | 3
Sorting algorithm | Arka/Tamal | 12 | 2 | [6 empty] | 2
Deduplication logic | Arka/Tamal | 12 | 3 | [6 empty] | 3
Stock verification | Arka/Tamal | 12 | 2 | [6 empty] | 2
History API wrapper | Arka/Tamal | 13 | 3 | [6 empty] | 3
Preference parsing | Arka/Tamal | 13 | 3 | [6 empty] | 3
Fallback logic | Arka/Tamal | 13 | 2 | [6 empty] | 2
Email builder | Arka/Tamal | 14 | 2 | [6 empty] | 2
Multi-recipient logic | Arka/Tamal | 14 | 2 | [6 empty] | 2
Failure handling | Arka/Tamal | 14 | 2 | [6 empty] | 2
Base behavior prompt | Arka/Tamal | 15 | 6 | [6 empty] | 1 | 5
Safety rules prompt | Arka/Tamal | 15 | 6 | [7 empty] | 6
Tool usage prompt | Arka/Tamal | 15 | 6 | [7 empty] | 6
Conversation style prompt | Arka/Tamal | 15 | 4 | [7 empty] | 4
Domain prompt | Arka/Tamal | 15 | 3 | [7 empty] | 3
Orchestrator role prompt | Arka/Tamal | 15 | 3 | [7 empty] | 3
Event planner prompt | Arka/Tamal | 15 | 5 | [7 empty] | 3 | 2
Product search prompt | Arka/Tamal | 15 | 3 | [8 empty] | 3
Supplies prompt | Arka/Tamal | 15 | 3 | [8 empty] | 3
Edge case tuning | Arka/Tamal | 15 | 3 | [8 empty] | 3
Routing tuning | Arka/Tamal | 15 | 2 | [8 empty] | 2
Regression tuning | Arka/Tamal | 15 | 1 | [8 empty] | 1
Agent unit tests | Arka/Tamal | 16 | 18 | [8 empty] | 16 | 2
Chain unit tests | Arka/Tamal | 16 | 20 | [9 empty] | 20
Tool unit tests | Arka/Tamal | 16 | 12 | [9 empty] | 8 | 4
Graph tests | Arka/Tamal | 16 | 8 | [10 empty] | 8
State tests | Arka/Tamal | 16 | 6 | [10 empty] | 6
Fixtures | Arka/Tamal | 16 | 8 | [10 empty] | 8
Conversation fixtures | Arka/Tamal | 17 | 8 | [10 empty] | 4 | 4
Mock responses | Arka/Tamal | 17 | 6 | [11 empty] | 6
Scenario tests | Arka/Tamal | 17 | 10 | [11 empty] | 10
Test harness | Arka/Tamal | 17 | 6 | [11 empty] | 6
Inventory mock | Arka/Tamal | 18 | 4 | [11 empty] | 4
History mock | Arka/Tamal | 18 | 3 | [12 empty] | 3
Email mock | Arka/Tamal | 18 | 3 | [12 empty] | 3
Test data generator | Arka/Tamal | 18 | 2 | [12 empty] | 2
Retry logic | Arka/Tamal | 19 | 4 | [12 empty] | 4
Rate limit handling | Arka/Tamal | 19 | 4 | [12 empty] | 4
Fallback logic | Arka/Tamal | 19 | 4 | [12 empty] | 4
Tracing integration | Arka/Tamal | 20 | 3 | [12 empty] | 3
Evaluation metrics | Arka/Tamal | 20 | 3 | [12 empty] | 3
Architecture documentation | Arka/Tamal | 21 | 8 | [12 empty] | 4 | 4
Developer setup guide | Arka/Tamal | 21 | 6 | [13 empty] | 6
Testing documentation | Arka/Tamal | 21 | 4 | [13 empty] | 4
API documentation | Arka/Tamal | 21 | 4 | [13 empty] | 4
Operational notes | Arka/Tamal | 21 | 2 | [13 empty] | 2
TOTAL HOURS |  |  | 410
Cell value = hours worked in that period ¦ Color = priority level
Priority 1 | Priority 2 | Priority 3 | Priority 4 | Priority 5