## 📅 Daily View
📅 Daily View ¦ Start: 06 Jan 2025 ¦ 6.0h/day ¦ Total: 97h
Summary | Assignee | Priority | Original Estimate (hrs) | Day1 6 Jan | Day2 7 Jan | Day3 8 Jan | Day4 9 Jan | Day5 10 Jan | Day6 13 Jan | Day7 14 Jan | Day8 15 Jan | Day9 16 Jan | Day10 17 Jan | Day11 20 Jan | Day12 21 Jan | Day13 22 Jan | Day14 23 Jan | Day15 24 Jan | Day16 27 Jan | Day17 28 Jan
Project Setup and Configuration | Dibyawan Trivedi | 1 | 6 | 6
Project Setup & Configuration | Somnath Bera | 1 | 10 |  | 6 | 4
DB Schema, Repository and Migrations | Somnath Bera | 1 | 20 |  |  | 2 | 6 | 6 | 6
New Badge variants | Dibyawan Trivedi | 2 | 2 | [6 empty] | 2
New Stepper Form Generic Component | Dibyawan Trivedi | 2 | 4 | [6 empty] | 4
New Tab Design | Dibyawan Trivedi | 2 | 2 | [7 empty] | 2
Add New Button Variant | Dibyawan Trivedi | 2 | 2 | [7 empty] | 2
Implement Contact Stage UI & Validation | Dibyawan Trivedi | 3 | 8 | [7 empty] | 2 | 6
Implement Target Stage UI & Validation | Dibyawan Trivedi | 3 | 6 | [9 empty] | 6
Page Navigation & Data Persistence | Dibyawan Trivedi | 3 | 4 | [10 empty] | 4
Implement Target Stage Endpoint and Validation | Somnath Bera | 3 | 8 | [10 empty] | 2 | 6
Contact Stage API and validation Implementation | Somnath Bera | 3 | 5 | [12 empty] | 5
Layout Initialization | Dibyawan Trivedi | 5 | 4 | [12 empty] | 1 | 3
KPI Dashboard Integration | Dibyawan Trivedi | 5 | 4 | [13 empty] | 3 | 1
Leads Data Table | Dibyawan Trivedi | 5 | 8 | [14 empty] | 5 | 3
Navigation & Routing | Dibyawan Trivedi | 5 | 4 | [15 empty] | 3 | 1
TOTAL HOURS
Cell value = hours worked in that period ¦ Color = priority level
Priority 1 | Priority 2 | Priority 3 | Priority 4 | Priority 5

## 📆 Weekly View
📆 Weekly View ¦ Start: 06 Jan 2025 ¦ 6.0h/day ¦ Total: 97h
Summary | Assignee | Priority | Original Estimate (hrs) | Wk1 6 Jan | Wk2 13 Jan | Wk3 20 Jan | Wk4 27 Jan | Wk5 3 Feb
Project Setup and Configuration | Dibyawan Trivedi | 1 | 6 | 6
Project Setup & Configuration | Somnath Bera | 1 | 10 | 10
DB Schema, Repository and Migrations | Somnath Bera | 1 | 20 | 14 | 6
New Badge variants | Dibyawan Trivedi | 2 | 2 |  | 2
New Stepper Form Generic Component | Dibyawan Trivedi | 2 | 4 |  | 4
New Tab Design | Dibyawan Trivedi | 2 | 2 |  | 2
Add New Button Variant | Dibyawan Trivedi | 2 | 2 |  | 2
Implement Contact Stage UI & Validation | Dibyawan Trivedi | 3 | 8 |  | 8
Implement Target Stage UI & Validation | Dibyawan Trivedi | 3 | 6 |  | 6
Page Navigation & Data Persistence | Dibyawan Trivedi | 3 | 4 |  |  | 4
Implement Target Stage Endpoint and Validation | Somnath Bera | 3 | 8 |  |  | 8
Contact Stage API and validation Implementation | Somnath Bera | 3 | 5 |  |  | 5
Layout Initialization | Dibyawan Trivedi | 5 | 4 |  |  | 4
KPI Dashboard Integration | Dibyawan Trivedi | 5 | 4 |  |  | 4
Leads Data Table | Dibyawan Trivedi | 5 | 8 |  |  | 5 | 3
Navigation & Routing | Dibyawan Trivedi | 5 | 4 |  |  |  | 4
TOTAL HOURS
Cell value = hours worked in that period ¦ Color = priority level
Priority 1 | Priority 2 | Priority 3 | Priority 4 | Priority 5