## Input
📋 GANTT INPUT SHEET
Start Date | 2026-04-02 | Format: YYYY-MM-DD
Hours Per Day | 16 | Productive hours per workday
💡 Both Daily and Weekly views are auto-generated — click the sheet tabs to switch between them.
Summary | Assignee | Priority | Estimated Hours | ← Row order within same priority = execution sequence
Design And requirement Analysis | Tamal | 1 | 10
Skeleton Setup | Arka | 1 | 10
Define overall system architecture | Tamal | 2 | 2
Define agent responsibilities | Arka | 2 | 1
Define chain responsibilities | Tamal | 2 | 1
Define tool interfaces | Arka | 2 | 1
Define state model | Tamal | 2 | 2
Setup graph project structure | Arka | 2 | 2
Implement graph node abstraction | Tamal | 2 | 2
Implement routing layer | Arka | 2 | 2
Implement node transitions | Arka/Tamal | 2 | 2
Implement session lifecycle | Arka/Tamal | 2 | 2
Integrate graph state store | Arka/Tamal | 2 | 1
Validate graph execution flow | Arka/Tamal | 2 | 1
Design session schema | Arka/Tamal | 3 | 4
Design state variable schema | Arka/Tamal | 3 | 2
Implement DB connection layer | Arka/Tamal | 3 | 2
Implement session storage | Arka/Tamal | 3 | 3
Implement conversation history storage | Arka/Tamal | 3 | 3
Implement state serialization | Arka/Tamal | 3 | 3
Implement state retrieval | Arka/Tamal | 3 | 3
Implement state update logic | Arka/Tamal | 3 | 3
Implement session recovery | Arka/Tamal | 3 | 3
Implement state expiration | Arka/Tamal | 3 | 2
DB error handling | Arka/Tamal | 3 | 2
Implement age verification flow | Arka/Tamal | 4 | 2
Implement intent classification | Arka/Tamal | 4 | 2
Implement ambiguity detection | Arka/Tamal | 4 | 2
Implement routing logic | Arka/Tamal | 4 | 2
Implement fallback routing | Arka/Tamal | 4 | 2
Event parameter extraction | Arka/Tamal | 5 | 2
Budget validation logic | Arka/Tamal | 5 | 2
Cocktail mode handling | Arka/Tamal | 5 | 2
Drink calculation logic | Arka/Tamal | 5 | 2
Category budget allocation | Arka/Tamal | 5 | 2
Inventory search orchestration | Arka/Tamal | 5 | 2
Package builder | Arka/Tamal | 5 | 2
Modification handling | Arka/Tamal | 5 | 1
Delivery detail collection | Arka/Tamal | 5 | 1
Product query parsing | Arka/Tamal | 6 | 2
Inventory lookup | Arka/Tamal | 6 | 2
Recommendation logic | Arka/Tamal | 6 | 2
Similar product suggestion | Arka/Tamal | 6 | 2
Supplies recommendation | Arka/Tamal | 7 | 2
OOS handling | Arka/Tamal | 7 | 2
Budget recalculation | Arka/Tamal | 7 | 2
Staffing offer | Arka/Tamal | 7 | 1
Menu email option | Arka/Tamal | 7 | 1
Info extraction chain | Arka/Tamal | 8 | 3
Budget viability chain | Arka/Tamal | 8 | 3
Cocktail adjustment chain | Arka/Tamal | 8 | 3
Drink calculation chain | Arka/Tamal | 8 | 3
Category budget chain | Arka/Tamal | 8 | 3
Inventory search chain | Arka/Tamal | 8 | 4
Package assembly chain | Arka/Tamal | 8 | 4
Budget compliance chain | Arka/Tamal | 8 | 3
Delivery chain | Arka/Tamal | 8 | 2
Query parsing chain | Arka/Tamal | 9 | 3
Inventory search chain | Arka/Tamal | 9 | 3
Recommendation chain | Arka/Tamal | 9 | 4
Similarity chain | Arka/Tamal | 9 | 3
Product request chain | Arka/Tamal | 9 | 2
Supplies search chain | Arka/Tamal | 10 | 3
OOS handling chain | Arka/Tamal | 10 | 3
Budget adjustment chain | Arka/Tamal | 10 | 3
Staffing chain | Arka/Tamal | 10 | 3
Menu email chain | Arka/Tamal | 10 | 2
Chain orchestration wiring | Arka/Tamal | 11 | 3
Inventory API wrapper | Arka/Tamal | 12 | 4
Product classification | Arka/Tamal | 12 | 3
Sorting algorithm | Arka/Tamal | 12 | 2
Deduplication logic | Arka/Tamal | 12 | 3
Stock verification | Arka/Tamal | 12 | 2
History API wrapper | Arka/Tamal | 13 | 3
Preference parsing | Arka/Tamal | 13 | 3
Fallback logic | Arka/Tamal | 13 | 2
Email builder | Arka/Tamal | 14 | 2
Multi-recipient logic | Arka/Tamal | 14 | 2
Failure handling | Arka/Tamal | 14 | 2
Base behavior prompt | Arka/Tamal | 15 | 6
Safety rules prompt | Arka/Tamal | 15 | 6
Tool usage prompt | Arka/Tamal | 15 | 6
Conversation style prompt | Arka/Tamal | 15 | 4
Domain prompt | Arka/Tamal | 15 | 3
Orchestrator role prompt | Arka/Tamal | 15 | 3
Event planner prompt | Arka/Tamal | 15 | 5
Product search prompt | Arka/Tamal | 15 | 3
Supplies prompt | Arka/Tamal | 15 | 3
Edge case tuning | Arka/Tamal | 15 | 3
Routing tuning | Arka/Tamal | 15 | 2
Regression tuning | Arka/Tamal | 15 | 1
Agent unit tests | Arka/Tamal | 16 | 18
Chain unit tests | Arka/Tamal | 16 | 20
Tool unit tests | Arka/Tamal | 16 | 12
Graph tests | Arka/Tamal | 16 | 8
State tests | Arka/Tamal | 16 | 6
Fixtures | Arka/Tamal | 16 | 8
Conversation fixtures | Arka/Tamal | 17 | 8
Mock responses | Arka/Tamal | 17 | 6
Scenario tests | Arka/Tamal | 17 | 10
Test harness | Arka/Tamal | 17 | 6
Inventory mock | Arka/Tamal | 18 | 4
History mock | Arka/Tamal | 18 | 3
Email mock | Arka/Tamal | 18 | 3
Test data generator | Arka/Tamal | 18 | 2
Retry logic | Arka/Tamal | 19 | 4
Rate limit handling | Arka/Tamal | 19 | 4
Fallback logic | Arka/Tamal | 19 | 4
Tracing integration | Arka/Tamal | 20 | 3
Evaluation metrics | Arka/Tamal | 20 | 3
Architecture documentation | Arka/Tamal | 21 | 8
Developer setup guide | Arka/Tamal | 21 | 6
Testing documentation | Arka/Tamal | 21 | 4
API documentation | Arka/Tamal | 21 | 4
Operational notes | Arka/Tamal | 21 | 2
410